Clinical Trial Project (& Risk) Management
Audit Check-List

1	Governance Committee	2

2	Project management	2

2.1	Regulatory Documentation	2

2.2	Procedures, instructions, forms, templates	2

2.3	Human resources devoted to Project Management	3

2.4	Project Management Tools	3

2.5	Project Management Activities	4

2.6	Change control	5

3	Study documentation management (TMF)	5

4	Risk Management for Clinical Studies	6

4.1	Risk mitigation measures taken for the XXX Clinical Trial	6

4.2	XXX Study Risk Analysis	6

4.2.1	Documents servant de support à l'analyse de risque	6

4.2.2	Risk Assessment	7

4.2.3	Criticity Assessment	7

4.2.4	Priority Assessment	7

4.2.5	Impact Categorization	7

4.3	Risk Analysis Table	8

4.4	Criticity 4 Risks	9

4.5	High Priority Risks	9

4.6	Conclusions	9

5	Version history of the audit report	9

6	Auditor's resume	9

A adapter en fonction de l'aspect qualification ou non de l'audit (étude déjà en cours ou pas)

# Governance Committee

Pas d'obligation réglementaire mais une façon de voir comment la structure gère les projets

☐ A Governance Committee is implemented

☐ for the study

☐ for all client's projects (global oversight)

☐ the Governance Committee composition and functioning is addressed:

☐ in a quality document

☐ in a Governance Plan or equivalent, addressing… (specify)

☐ Regular meetings are organized (frequency?) and documented

Detail communication flows

Observation n° Grade

Blablabla Main audit standards

Suggestions

# Project management

## Regulatory Documentation

☐ The applicable requirements and recommendations for the process are documented, easily available, known by the concerned staff (training evidences).

☐ A system which guarantees the update of the regulatory documentation exists (regulatory Intelligence).

## Human resources devoted to Project Management

☐ There is a controlled system to manage operational human resources (i.e.: staff workload assessment, update, availabilities, etc.) under the responsibility of [function].

☐ The staff workload/availability is revised with an appropriate frequency.

☐ There is a specific tool to manage human resources.

☐ The allocation of resource is based on the following criteria:

Maximum of x studies per PM / other?

Systematic allocation of administrative support for each project in addition to the Project Manager

Systematic allocation of a Project Director depending on the project size

PM assigned depending on their therapeutic area knowledge or other criteria.

☐ Human resources allocated to the project are sufficient, adapted to the project conditions and trained on:

Regulatory requirements

Protocol

Pathology

IMP

Applicable procedures, instructions, templates use, etc.

☐ The Project Team is identified.

☐ Composition of the Project Team:

Check team members seniority

☐ The list identifying the Project Team is up to date and superseded versions are available.

☐ The study-related duties and functions are appropriately allocated.

☐ The Project Manager is the "pilot" of the study and the main point contact for the Sponsor.

☐ A back-up system exists to guarantee continuity of overall management of the study.

In case of planned vacations

In case of unplanned leave.

☐ There is a documented handover process in case of Project Manager change (traceability of transferred activities, study training documentation, handover dates, …).

## Procedures, instructions, forms, templates

☐ There is an up-to-date list of applicable procedures for the study.

☐ The procedures applicable for Project Management are:

International procedures of the Sponsor:

Local procedures of the Sponsor:

Procedures of the Clinical Research Organization:

☐ There are study-specific SOPs/templates/forms designed for each project and available for the study team.

## Project Management Tools

☐ There are tools for project management to ensure compliance with the objectives (FPI, recruitment rate), the timelines, the budget, the follow-up of subcontractors

Briefly describe the too(s)l (name, activities managed through the tool, who can access the tool to enter data/to check/…)

☐ KPI are identified, collected at the expected frequency and shared/discussed with the Sponsor.

☐ There is a Project Management Plan or equivalent

☐ issued prior the start of the study

☐ appropriately updated during the course of the study.

☐ There are other specific plans available (Quality Plan, Communication Plan, TMF Management Plan,…).

☐ specific tools for budget management?

☐ There is a paper TMF/an eTMF allowing the PM to have a proper access to information.

access conditions for PM?

☐ Security of used systems (access, backup, standby system, validation if applicable, etc.) cf CL VSI pour plus de détails

☐ There is a system for study electronic files management guaranteeing an easy and secure access to study information for all authorized staff:

☐ predefined architecture shared by all the projects,

☐ filing rules (order, delay, responsible),

☐ electronic documents identification rules,

☐ quality control…

☐ There is a system for study related emails management guaranteeing an easy and secure access to study information for all authorized staff:

☐ predefined architecture shared by all the projects,

☐ filing rules (order, delay, responsible),

☐ electronic documents identification rules,

☐ quality control…

☐ Project quality controls are carried out, are documented, are available and are transmitted to the Sponsor.

## Project Management Activities

☐ Project management is addressed in the procedure "…" (Field of application, reference documents, responsibilities, Sponsor's involvement, quality controls, staff training,…)

☐ Internal project meetings are regularly held and corresponding minutes are available.

☐ Project meetings with the Sponsor are regularly held and corresponding minutes are available.

☐ Frequency of project meetings is appropriate.

☐ The progress reports are carried out throughout the trial, are available and are transmitted to the Sponsor.

☐ Project quality controls are carried out, are documented, are available and are transmitted to the Sponsor.

☐ Guidelines to fill out the study documentation are defined and described.

☐ Project Management tools are completed in a timely manner.

☐ Changes having a significant impact on the conduct of the study are identified and an impact analysis is performed.

☐ Non-conformities and protocol deviations are identified and managed until resolution.

> examples?

☐ Non compliances are shared with the Sponsor

5.20. Noncompliance 5.20.1. Noncompliance with the protocol, SOPs, GCP, and/or applicable regulatory requirement(s) by an investigator/institution, or by member(s) of the sponsor's staff should lead to prompt action by the sponsor to secure compliance. ADDENDUM If noncompliance that significantly affects or has the potential to significantly affect human subject protection or reliability of trial results is discovered, the sponsor should perform a root cause analysis and implement appropriate corrective and preventive actions. GCP ICH E6 R2

☐ There is a global actions plan to manage decisions and actions throughout the study.

☐ Communication lines are defined

Internal communication

communication with other parties involved in the study

communication with investigational sites (e.g. newsletters)

reporting to Sponsor

escalation process,…

☐ Which measures are implemented to secure exchange of information/listings/data with the sponsor and 3rd parties?

## Change control

☒ SOP (see the table below)

☐ Change identification and assessment

☐ Impact of change:

are all aspects of the trial / delegated services considered for the impact assessment ?

including impact of the change on the trial risk assessment, contractual documentation …

☐ Documentation

| Change Control - Impact Analysis |  |  |  |  |
| --- | --- | --- | --- | --- |
| SOP title, ID, version |  |  |  |  |
| Steps |  | CPL | CRO |  |
| ☐ Change input |  |  |  |  |
| ☐ Change analysis |  |  |  |  |
| ☐ Change decision |  |  |  |  |
| ☐ Categorisation of changes |  |  |  |  |
| ☐ Flow of information (dispatch of information) |  |  |  |  |
| ☐ Global and specific Impact Analyses |  |  |  |  |
| ☐ CAPA management (decision of action, planning, dispatch, performance, response, check, documentation) |  |  |  |  |
| Comments |  |  |  |  |

# Study documentation management (TMF)

Definition of roles and responsibilities distributions between Sponsor and CRO ?

SOP and/or TMF management Plan

Table of content of the TMF based on GCP ICH §8 or on the TMF reference Model from the DIA?

Trial documentation location specified ?

Periodic TMF QC ? documented ?

# Risk Management for Clinical Studies

☐ There is "Risk Management Plan" (or equivalent).

☐ Key study-related risks have been identified and assessed.

☐ Risk mitigation measures, along with tolerance limits, have been determined and implemented.

☐ The "Risk Management Plan" is appropriately updated.

For the XXX study, the following risks are identified:

## Risk mitigation measures taken for the XXX Clinical Trial

The following risk mitigation measures have been taken:

## XXX Study Risk Analysis

L'objectif de ce document est de:

- caractériser chaque risque identifié (probabilité de survenue, conséquences, criticité, priorité), sur la base de l'Inventaire des Risques,

- évaluer ses causes et ses conséquences possibles.

Hypothèses formulées à la base de l'analyse de risque :

- à compléter

### Documents servant de support à l'analyse de risque

| Document | Reference | Version |
| --- | --- | --- |

### Risk Assessment

| Probability of occurrence | Consequences | Criticity | Priority |
| --- | --- | --- | --- |
| - P0 - Very rare - P1 - Rare - P2 - Occasional - P3 - Frequent - P4 - Very frequent | - C0 - Insignificant - C1 - Minor - C2 - Important - C3 - Major - C4 - Critical | - Cr1 : Criticity 1 - Cr2 : Criticity 2 - Cr3 : Criticity 3 - Cr4 : Criticity 4 | - Pr1 : Low Priority - Pr2 : Medium Priority - Pr3 : High Priority |

### Criticity Assessment

| Occurrence Probability | Consequences |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | C0 Insignificant | C1 Minor | C2 Important | C3 Major | C4 Critical |
| P4 - Very frequent (p≈1) | Cr2 | Cr3 | Cr3 | Cr4 | Cr4 |
| P3 - Frequent | Cr2 | Cr2 | Cr3 | Cr3 | Cr4 |
| P2 - Occasional | Cr1 | Cr2 | Cr2 | Cr3 | Cr3 |
| P1 - Rare | Cr1 | Cr1 | Cr2 | Cr2 | Cr3 |
| P0 - Very rare (p≈0) | Cr1 | Cr1 | Cr1 | Cr2 | Cr2 |

### Priority Assessment

| Criticity | Detectability |  |  |
| --- | --- | --- | --- |
|  | D0 Obvious | D1 Moderately Detectable | D2 Undetectable |
| Cr4 - Critical | Pr3 | Pr3 | Pr3 |
| Cr3 - Major | Pr2 | Pr3 | Pr3 |
| Cr2 - Important | Pr2 | Pr2 | Pr3 |
| Cr1 - Minor | Pr1 | Pr2 | Pr2 |

### Impact Categorization

- R: Regulatory

- B: Business

## Risk Analysis Table

| Activity | Risk Ref. | Risk | Cause | Consequence | Preventive and Protective Actions | Residual Risk Assessment |  |  |  |  |  | Degraded Mode |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Impact | Prob. | Conseq. | Criticity | Detect. | Priority |  |

## Criticity 4 Risks

| Category | Risk Ref. | Risk |
| --- | --- | --- |

## High Priority Risks

| Category | Risk Ref. | Risk |
| --- | --- | --- |

## Conclusions

# Version history of the audit report

| Version | Date | Comments |
| --- | --- | --- |
| V0.1 |  | Livraison de la version préliminaire pour relecture du commanditaire de l'audit Delivery of the draft version for review by the audit sponsor |
| V1.0 |  | Delivery of the signed version after receipt of the audit sponsor's comments received on …. |

# Auditor's resume